## Risk Register
Risk ID | Risk Description | Impact | Likelihood | Risk Rating | Mitigation Strategy | Owner | Status
R1 | Unauthorized admin access | High | Medium | High | Use MFA and enforce role-based access control (RBAC) using PIM. | IAM Team | Open
R2 | Phishing attack targeting staff | High | High | Critical | Conduct mandatory security awareness training and simulated phishing campaigns. | Security Team | Open
R3 | Outdated software vulnerabilities | Medium | High | High | Implement a monthly patch cycle and automatic software updates. | IT Operations | Open
R4 | Data leakage by guest users | High | Medium | High | Restrict external sharing and configure guest access governance policies. | IAM Team | Open
R5 | Audit logs not retained for 90 days | Medium | Medium | Medium | Set log retention policy to 90 days in Entra ID and verify with compliance team. | Compliance Officer | Open
R6 | Weak password practices | High | Medium | High | Implement password protection policy and enforce MFA. | Security Team | Open
R7 | Unapproved cloud app usage | Medium | Medium | Medium | Use MCAS or Defender for Cloud Apps to detect and block shadow IT. | Cloud Security | Open
R8 | Inactive user accounts | Low | High | Medium | Use access reviews and automate deactivation of stale accounts. | IAM Admin | Open
R9 | Malware outbreak in shared drives | High | Low | Medium | Deploy endpoint protection and scan shared resources weekly. | IT Support | Open
R10 | Loss of critical data due to failed backup | High | Low | Medium | Verify daily backup jobs and test restore process monthly. | IT Backup Admin | Open